## Sheet1
SL | Task | Owner | Team | Status | Dead Line
General Tasks
1 | Percentile for all the charts | Sameer | Sameer Shreya | Awaiting for guidance from Mgmt | 2024-01-08
2 | Drill down for all Charts | Sameer | Sameer Shreya | Done
3 | Moving date time to top | Vaseema | Vaseema, Shravani | Done
4 | SP for Percentile for all the charts and its drilldown | Niti | Niti | In Progress | ASAP
5 | Submissions/Quotes/ day bar chart by LOB | Sameer |  |  | 2024-06-10
6 | Errors count by Page bar chart by LOB | Sameer |  | Done | 2024-06-08
7 | Grid to provide - Agency Login ID - Agency Name - Agency login time - Session duration Session ID (Session ID should be linked to drilldown session activity) | Sameer |  | Awaiting for guidance from Mgmt | TBD
AI/ML Tasks
8 | AI/ML team needs to finaise the Model | Madhura | Madhura Karthik | In Progress | TBD
9 | -Capture JSON Records: Retrieve and collect JSON records for each URL where the chatbot will be displayed. | Vaseema | Vaseema Shravani | Done
10 | -Pass Data to OpenAI Assistant Service: Submit the collected JSON data to the OpenAI Assistant Service for processing. | Vaseema | Vaseema Shravani | Done
11 | -Process Data: Utilize the OpenAI Assistant Service to generate a response based on the provided JSON data. | Vaseema | Vaseema Shravani | Done
12 | -Format Response: Convert the response from the OpenAI Assistant Service into a text format suitable for display. | Vaseema | Vaseema Shravani | Done
13 | -Update Chatbot View: Integrate the formatted text response into the chatbot interface for user interaction. | Vaseema | Vaseema Shravani | Done
Business Process Improvement
14.a | - Anomalist or unusual Quote response time (Some time customers are experiencing timeout) - Improve response time | Sameer | Sameer | Done
14.b | - Improve response time | MGMT |  | Awaiting for guidance from Mgmt | TBD
15.a | - Unusual time spent to fill the forms ( Highest time spent on page list- Based on Priority) | Sameer |  | Done
15.b | - Provide insight into the anomalies. (Agency is not writing business because of these issues | AI/ML?
15.c | - Generates alerts ahead of time and pro-actively we should be able to address it) | AI/ML?
16 | - Number of Errors by Category and High number issues list (Based on the priority might be the by product of the model) (Based on the impact to the customer) | Sameer |  | Awaiting for guidance from Mgmt | TBD
Agency Performance Improvements
17 | - Low number of submissions, Quotes and Binds (By Agency) | Vaseema | Vaseema Shravani Niti | In Progress | 2024-08-09
18 | - Less Premium in revenue generated by Agency | Vaseema | Vaseema Shravani Niti | In Progress | 2024-08-09
IT Improvements
19 | - Number of Errors Category and High number issues list (Based on the priority ) | Sameer |  | In Progress | TBD
Fraud Detection
20 | - Recognize bad submission based on the behavior and data - Stop submissions | AI/ML?
21 | - Recognize bad Claims based on the data - Stop or alter team to address these claims | AI/ML?
Marketing team effort to retain existing customers and gain new business
22 | - Predictive model understand the Customer drop out and predict the trend so that we can retain the customers | ML?
23 | - Understand the customer better based on that data and give marketing visibility to present | ML?
24 | Authentication & Authorization | MGMT
25 | Mock Guidewire Data to generate prospect journey between channels
26 | Reskin with the new design for chat bot | Vaseema | Vaseema Shravani | Completed | 2024-08-06
27 | Apply the assistant to all pages | Vaseema | Vaseema Shravani | In Progress | 2024-08-14