## Android App
Sheet Name | Description | Test Steps | Expected Output | Original Status | TechPundits Test Results | TechPundits Bug Fixes | Test Results Post Bug Fix | TechPundits Comments
ForgotReset Password | Verify entering the same password as the old password | 1. Navigate to the reset password page 2. Enter the user's current/old password in both fields 3. Click the submit button | 1. Form should not be submitted 2. A validation message should appear indicating that the new password cannot be the same as the old password 3. User should be prompted to choose a different password | Pass | Fail | In-progress |  | Validation message does not appear when user's current /old password is entered in both fields. It accepts them and displays the message 'Password updated successfully' Also, user is not prompted to choose a different password
Receptionist Signup | Verify welcome message or username display | 1. Login with a receptionist account 2. Observe the welcome screen | 1. A welcome message or the username should be displayed 2. The message should be personalized with the user's name | Pass | Fail | Fixed | Pass | When logged in with a receptionist account, the welcome screen is displayed, but does not show a personalized message with the user's name.
Receptionist Signup | Verify visitor management page access from check-in option | 1. Click on the check-in option from the welcome screen 2. Observe the visitor management page | 1. User should be navigated to the visitor management page 2. Visitor management page should load completely 3. All visitor management functions should be accessible | Pass | Fail | Fixed | Pass | When the check-in option from the welcome screen is clicked, user is navigated to the Visitor Information page. Visitor management functions are not displayed
Check-in | Verify navigation after confirming visitor details | 1. Navigate to review and confirmation screen 2. Click on the confirm button | User is navigated to the notification status screen followed by the visitor badge display within 2-3 seconds | Pass | Fail | Fixed | Pass | When Confirm button is clicked and an email is sent to host, the visitor badge is not displayed
Check-in | Verify visitor badge printing process | 1. Complete visitor check-in process 2. Reach the confirmation screen where badge is displayed | Visitor badge is printed by the printer | Pass | Fail | In-progress |  | Visitor badge printing - not tested as confirmation screen where badge is displayed does not appear
Check-in | Verify cancellation of check-in process | 1. Start the visitor check-in process 2. Click on cancel/back button at any stage | User should be navigated back to the home/landing page | Pass | Fail | In-progress |  | User can only click the Back button and navigate to the previous page. It does not navigate to the home/landing page when back button is clicked.
Check-in | Verify visitor badge includes all required information | 1. Complete visitor check-in process 2. View the generated visitor badge | Badge should display visitor name, host name, date, time, and any other required information | Pass | Fail | Fixed | Pass | Badge displays all required information of the Visitor
Check-in | Verify visitor badge includes all required information | 1. Complete visitor check-in process 2. View the generated visitor badge | Badge should display visitor name, host name, date, time, and any other required information | Pass | Fail | Fixed | Pass | Visitor badge is not getting displayed
Check-out | Verify checkout status is updated in system | 1. Successfully check out a visitor 2. Check visitor status in the system (via admin panel or database) | Visitor status should be updated to 'checked out' with accurate checkout timestamp | Pass | Fail | Fixed | Pass | When the visitor is checked out, it displays the screen for Check-out complete. In the admin panel, it shows the check-out time, but shows the Visitor Request Status as ‘Pending’
Recept. Sign up New | First Name Validation - Minimum Length | 1. Navigate to registration page 2. Enter First Name: J 3. Enter Last Name: Doe 4. Enter Valid Email: john.doe@company.com 5. Enter Valid Phone Number: +1234567890 6. Select Location: New York 7. Select Entity: Hospital 8. Enter Strong Password: P@ssw0rd123! 9. Confirm Password: P@ssw0rd123! 10. Click Submit | Validation message appears: First name must be at least 2 characters long | Pass | Fail | Fixed | Pass | It accepts a First Name having a single character and creates the account
Recept. Sign up New | Location Validation - Not Entered | 1. Navigate to registration page 2. Enter First Name: John 3. Enter Last Name: Doe 4. Enter Valid Email: john.doe@company.com 5. Enter Valid Phone Number: +1234567890 6. Leave Location Not Entered 7. Select Entity: Hospital 8. Enter Strong Password: P@ssw0rd123! 9. Confirm Password: P@ssw0rd123! 10. Click Submit | Validation message appears: Location is required | Pass | Fail |  |  | The Location field is not present in the form
Recept. Sign up New | Entity Validation - Not Selected | 1. Navigate to registration page 2. Enter First Name: John 3. Enter Last Name: Doe 4. Enter Valid Email: john.doe@company.com 5. Enter Valid Phone Number: +1234567890 6. Select Location: New York 7. Leave Entity unselected 8. Enter Strong Password: P@ssw0rd123! 9. Confirm Password: P@ssw0rd123! 10. Click Submit | Validation message appears: Entity is required | Pass | Fail |  |  | There is no option to select an entity

## Admin Console
Sheet Name | Description | Test Steps | Expected Output | Original Status | TechPundits Test Results | TechPundits Comments
Host Management | Verify filter section functionality | 1. Navigate to the host management section. 2. Click on the "Filter" section/button. | A dropdown menu should open, displaying all entities available for filtering. | Pass | Fail | Advanced filter functionality is not implemented on the Host Management page. Only basic search is available.
Host Management | Verify validation for missing entity selection | 1. Navigate to the host creation page. 2. Enter host name and email but do not select an entity. 3. Click the "Submit" button. | A validation message should appear indicating that an entity must be selected. | Pass | Fail | Validation for entity selection is not working as expected. When the host name and email are entered without selecting an entity, the form allows submission without displaying a validation message. Proper validation should be implemented to ensure entity selection is mandatory.
General Setting | Verify prevention of invalid file type in image fields | 1. Navigate to the site settings page. 2. Attempt to upload a video or audio file in an image field. 3. Click the 'Submit' button. | The application should prevent the upload and display an error message indicating invalid file type. | Pass | Fail | Any file type (.docx, .pdf, .txt, .csv, .gz, .rar) is being accepted and the message 'Site settings have been updated successfully' is being displayed on clicking the 'Submit' button
General Setting | Verify validation for invalid email format | 1. Navigate to the site settings page. 2. Enter an invalid email address in the email field. 3. Click the 'Submit' button. | A validation message should appear indicating the invalid email format, and the settings should not be updated. | Pass | Fail | (User@gmail, .john@example.com)-> Accepted (User.gmail.com, @gmail.com, gmail.com, user@, user yahoo.com, .john@yahoo.com, john@-domain.com, john@.com john..doe@example.com, john@.com, john@domain-.com, john@ john@domain..co.uk, user) -> Please enter a valid email address
Logout | Verify after clicking on the back button and perfrom any action | 1. Click on the back button 2. Click on any of the option | User is logged out from the admin panel and redirected to the login page. | Pass | Fail | When 'Logout' button is clicked, user is redirected to login page. And, when the back button is clicked and changes are made, for example, to the Site Name and 'Submit' button is clicked, the following alert message is displayed: DataTables warning: table id=users-table - Invalid JSON response. For more information about this error, please see http://datatables.net/tn/1 Subsequent operations are not performed and user is redirected to login page.