## Login
Description | Test Steps | Expected Output | Status | Test Status | Comments | Neha's Comments
Verify successful login with valid credentials | 1. Navigate to the receptionist login page 2. Enter a valid email in the username field 3. Enter a valid password in the password field 4. Click on the Submit button | 1. User should be successfully logged in 2. User should be redirected to the dashboard or home page 3. A welcome message should be displayed | Pass | Pass | Successful login with valid credentials
Verify login with valid email and invalid password | 1. Navigate to the receptionist login page 2. Enter a valid email in the username field 3. Enter an invalid password in the password field 4. Click on the Submit button | 1. User should not be logged in 2. A validation error message should appear on the page 3. The message should indicate that the password is incorrect | Pass | Pass | For invalid password, it displays the error message regarding a valid password format
Verify login with invalid email and valid password | 1. Navigate to the receptionist login page 2. Enter an invalid email in the username field 3. Enter a valid password in the password field 4. Click on the Submit button | 1. User should not be logged in 2. A validation error message should appear on the page 3. The message should indicate that the email is incorrect | Pass | Pass | For invalid email, it displays the message that the email does not exist.
Verify login with invalid email and invalid password | 1. Navigate to the receptionist login page 2. Enter an invalid email in the username field 3. Enter an invalid password in the password field 4. Click on the Submit button | 1. User should not be logged in 2. A validation error message should appear on the page 3. The message should indicate that the credentials are incorrect | Pass | Pass | Displays the error message as “The email does not exist” | Validation message says no email exists (correct but should it say, “email or password incorrect”)
Verify login with empty email and valid password | 1. Navigate to the receptionist login page 2. Leave the email field empty 3. Enter a valid password in the password field 4. Click on the Submit button | 1. User should not be logged in 2. A validation error message should appear on the page 3. The message should indicate that the email field is required | Pass | Pass | User is not logged and displays the error message “Please enter email address”
Verify login with valid email and empty password | 1. Navigate to the receptionist login page 2. Enter a valid email in the username field 3. Leave the password field empty 4. Click on the Submit button | 1. User should not be logged in 2. A validation error message should appear on the page 3. The message should indicate that the password field is required | Pass | Pass | Displays the message to enter the password
Verify login with empty email and empty password | 1. Navigate to the receptionist login page 2. Leave the email field empty 3. Leave the password field empty 4. Click on the Submit button | 1. User should not be logged in 2. A validation error message should appear on the page 3. The message should indicate that both fields are required | Pass | Pass | Displays only the error message “Please enter email address” | Validation message only talks about email (say both fields are required to be filled in)
Verify login with special characters in email field | 1. Navigate to the receptionist login page 2. Enter special characters (e.g., @#$%) in the email field 3. Enter a valid password in the password field 4. Click on the Submit button | 1. User should not be logged in 2. A validation error message should appear on the page 3. The message should indicate that the email format is invalid | Pass | Pass | Displays the error message indicating that the email format is invalid.
Verify login with very long email input | 1. Navigate to the receptionist login page 2. Enter an extremely long string in the email field (e.g., 1000 characters) 3. Enter a valid password in the password field 4. Click on the Submit button | 1. A validation message should be appearing on the page. | Pass | Pass | For a very long email input, it displays the error message “Please enter a valid email address”
Verify login with very long password input | 1. Navigate to the receptionist login page 2. Enter a valid email in the username field 3. Enter an extremely long string in the password field (e.g., 1000 characters) 4. Click on the Submit button | 1. A validation message should be appearing on the page. | Pass | Pass | For a very long password, displays a validation message giving the valid password format
Verify password masking functionality | 1. Navigate to the receptionist login page 2. Enter a password in the password field 3. Observe the password field | 1. The password should be masked (displayed as dots or asterisks) 2. The actual characters should not be visible | Pass | Pass | Password is masked and displayed as dots, making the actual characters to not be visible
Verify 'Show Password' functionality | 1. Navigate to the receptionist login page 2. Enter a password in the password field 3. Click on the 'Show Password' icon or checkbox (if available) | 1. When clicked, the password should become visible 2. When clicked again, the password should be masked again | Pass | Pass | Clicking on the ‘Show Password’ causes the password to become visible or be masked again.
Verify accessibility of login form with keyboard navigation | 1. Navigate to the receptionist login page 2. Use Tab key to navigate through the form elements 3. Use Enter key to submit the form with valid credentials | 1. User should be able to navigate through all form elements using the Tab key 2. User should be able to submit the form using the Enter key 3. Login should be successful with valid credentials | Pass | Pass | Using the Tab key for navigation through the form elements and Enter key to submit the form was successful | Able to navigate with Tab to the next line but still not able to submit the form with enter
Verify login page UI elements | 1. Navigate to the receptionist login page 2. Observe all UI elements | 1. All required elements should be present: email field, password field, submit button 2. Optional elements may include: 'Remember Me' checkbox, 'Forgot Password' link 3. All elements should be properly aligned and formatted | Pass | Pass | All elements are properly aligned and formatted
Verify login with case-sensitive email | 1. Navigate to the receptionist login page 2. Enter a valid username with different case (e.g., if username is 'Receptionist1', enter 'receptionist1') 3. Enter a valid password 4. Submit the form | 1. If the system is designed to be case-insensitive for usernames/emails, login should be successful 2. If case-sensitive, the appropriate error message should be displayed | Pass | Pass | Case-insensitivity for username/emails was successful
Verify login with case-sensitive password | 1. Navigate to the receptionist login page 2. Enter a valid email 3. Enter a valid password with incorrect case (e.g., if password is 'Password123', enter 'password123') 4. Submit the form | 1. The login should fail as passwords are typically case-sensitive 2. An appropriate error message should be displayed | Pass | Pass | Case-sensitivity for passwords displayed the error message | Login does fail but error message says password contains … which is okay but a more appropriate message would be, incorrect password
Verify login after back button usage | 1. Login successfully 2. Navigate to another page 3. Click the browser's back button 4. Attempt to use the application | 1. User should remain logged in 2. User should not be able to see the login page again unless explicitly logged out | Pass | Pass | User remains logged in when the browser’s back button is clicked until logged out
Verify form validation for email format. | 1. Navigate to the receptionist login page 2. Enter an invalid email format (e.g., 'user@' or 'user.com') 3. Enter a valid password 4. Submit the form | 1. Form should validate email format 2. An appropriate error message should be displayed 3. Form should not be submitted until corrected | Pass | Pass | Gives an error message when invalid email format like (user@) is entered.

## ForgotReset Password
Description | Test Steps | Expected Output | Status | Test Status | Comments | Neha's Comments
Verify accessibility of Forgot Password link | 1. Navigate to the receptionist login page 2. Locate the 'Forgot Password' link 3. Click on the 'Forgot Password' link | 1. The 'Forgot Password' link should be clearly visible on the login page 2. The link should be clickable 3. User should be redirected to the password recovery page | Pass | Pass | Forgot Password' link is clearly visible and clickable. Sends a reset link to the email id
Verify UI elements on the forgot password page | 1. Navigate to the forgot password page 2. Observe all UI elements on the page | 1. Page should have a field to enter email address 2. Page should have a submit/send button 3. Page should have a back/cancel button to return to login page 4. All elements should be properly aligned and formatted 5. Page should have proper instructions explaining the password recovery process | Pass | Pass | Forgot password link page has a field for email address, Send button, back button, and proper instructions explaining the password recovery process. Elements are properly aligned and formatted.
Verify submitting with an empty email field | 1. Navigate to the forgot password page 2. Leave the email field empty 3. Click the submit button | 1. Form should not be submitted 2. A validation message should appear indicating that email is required | Pass | Pass | Leaving the password field empty displays validation message indication email is required
Verify submitting with an invalid email format | 1. Navigate to the forgot password page 2. Enter an invalid email format (e.g., 'user@', 'user.com', 'user@domain') 3. Click the submit button | 1. Form should not be submitted 2. A validation message should appear indicating that the email format is invalid | Pass | Pass | When an invalid email is entered, form is not submitted and a validation message appears indicating that the email format is invalid.
Verify submitting with an email that doesn't exist in the system | 1. Navigate to the forgot password page 2. Enter an email that is not registered in the system 3. Click the submit button | 1. A generic message should appear saying 'If the email exists in our system, a password reset link has been sent' 2. No actual email should be sent | Pass | Pass | When an email that doesn't exist in the system is entered, it gives the messge 'Please enter a valid email or password'
Verify submitting with a valid registered email | 1. Navigate to the forgot password page 2. Enter a valid email that is registered in the system 3. Click the submit button | 1. A success message should appear saying 'If the email exists in our system, a password reset link has been sent' 2. A password reset link should be sent to the provided email address 3. The email should be received within a reasonable time frame | Pass | Pass | When a valid email is entered and Send Reset Link button is clicked, a pasword reset link is sent to the provided email address. The email is received within a reasonable time frame.
Verify multiple password reset requests for the same email | 1. Navigate to the forgot password page 2. Enter a valid registered email 3. Submit the form 4. Repeat steps 1-3 within a short time period | 1. System should handle multiple requests without errors 2. Either: - New reset links should be sent, invalidating previous ones, or - A message should indicate that a reset link was recently sent and to check email or wait before requesting again | Pass | Pass | When a valid email is entered and Send Reset Link button is clicked multiple times within a short time period, it gives the error message 'Something went wrong. Please try again later'. But an passord reset link gets sent to the email.
Verify the ability to cancel the forgot password process | 1. Navigate to the forgot password page 2. Click on the cancel/back button or link | 1. User should be redirected back to the login page 2. No password reset process should be initiated | Pass | Pass | User is redirected back to the login page when back button is clicked and the password reset process is not initiated.
Verify forgot password with special characters in email | 1. Navigate to the forgot password page 2. Enter a valid email containing special characters (e.g., test.user+tag@domain.com) 3. Submit the form | 1. System should handle special characters in email correctly 2. Password reset process should be initiated successfully | Pass | Pass | When a valid email address containing special characters is entered, it is handled correctly and displays the message 'The selected email is invalid'.
Verify password reset process with inactive/disabled accounts | 1. Navigate to the forgot password page 2. Enter an email associated with an inactive or disabled account 3. Submit the form | 1. For security reasons, system should not indicate that the account is inactive 2. Either no email should be sent or an email explaining the account status should be sent 3. Standard success message should still be displayed | Pass | Pass | When an email associated with an inactive or disabled account is entered, the Reset Password is received on that email. And when that link is clicked, it displays a page with new and confirm password field. When Reset Password is clicked on that page, it displays Password Rest Successfully. When user tries to login with new password, it displays the message that saying 'Your account has been deactivated'
Verify password validation during reset | 1. Follow the password reset link from email 2. Enter a new password that doesn't meet security requirements 3. Submit the form | 1. Form should not be submitted 2. Validation errors should be displayed explaining password requirements 3. User should be able to correct and resubmit | Pass | Pass | Form is not submitted when new password does not meet the password requirements. Only after the user corrects the password, he can resubmit it
Verify password and confirm password match validation | 1. Follow the password reset link from email 2. Enter a new password 3. Enter a different password in the confirm password field 4. Submit the form | 1. Form should not be submitted 2. Validation error should be displayed indicating passwords don't match 3. User should be able to correct and resubmit | Pass | Pass | Form is not submitted when passwords do not match the password requirements. User can correct them and then resubmit it
Verify user notification after successful password reset | 1. Complete the password reset process successfully 2. Observe any notifications | 1. User should receive confirmation that the password has been reset 2. Optionally, a notification email confirming password change may be sent | Pass | Pass | User does not receive confirmation that the password has been reset. Only a message is displayed in the browser saying 'Pasword updated successfully' | Login does fail but error message says password contains … which is okay but a more appropriate message would be, incorrect password
Verify reset link usage after successful reset | 1. Complete the password reset process successfully 2. Try to use the same reset link again | 1. The reset link should be invalidated after successful use 2. Attempting to use it again should result in an error message 3. User should be directed to request a new reset link if needed | Pass | Pass | When the same reset link is used again, it accepts the new and confirm passwords. When the Reset Password is clicked, it displays the message 'Invalid Password Token' User is not directed to request a new reset link. | Same link allowed to use however when tried to change password on it says invalid token but there is no redirection to request new reset request — should not even allow for reopening of same reset link after use, should also time out after some time.
Verify UI elements on the reset password page | 1. Navigate to the reset password page via the link received in email 2. Observe all UI elements on the page | 1. Page should have fields for new password and confirm password 2. Page should have a submit/save button 3. Password requirements should be clearly displayed 4. All elements should be properly aligned and formatted | Pass | Pass | The reset password page has the fields for new and confirm passwords, Reset Password button that are properly aligned and fomatted. Password requirement are clearly displayed when user enters a password that does not meet the requirements. | UI is good except — masking works but I think the eye should be cancelled when its the dots and not canceled when you are able to see the password
Verify submitting with empty password fields | 1. Navigate to the reset password page 2. Leave both new password and confirm password fields empty 3. Click the submit button | 1. Form should not be submitted 2. Validation messages should appear indicating that both fields are required | Pass | Pass | When both new and confirm password fields are empty and Reset Password is clicked, validation message appears indicating both fields are required.
Verify submitting with only new password field filled | 1. Navigate to the reset password page 2. Enter a value in the new password field 3. Leave the confirm password field empty 4. Click the submit button | 1. Form should not be submitted 2. A validation message should appear indicating that confirm password is required | Pass | Pass | Form is not submitted when a value is entered in confirm password field and the new password field if left empty. It displays the message saying 'Please enter confirm password'.
Verify submitting with only confirm password field filled | 1. Navigate to the reset password page 2. Leave the new password field empty 3. Enter a value in the confirm password field 4. Click the submit button | 1. Form should not be submitted 2. A validation message should appear indicating that new password is required | Pass | Pass | Form is not submitted when a value is entered in new password field and confirm password field is lfet empty. It displays the message saying 'Please a new password'.
Verify entering different passwords in new password and confirm password fields | 1. Navigate to the reset password page 2. Enter a password in the new password field 3. Enter a different password in the confirm password field 4. Click the submit button | 1. Form should not be submitted 2. A validation message should appear indicating that passwords do not match 3. User should not be able to change their password until corrected | Pass | Pass | Form is not submitted when a value is entered when different passwords are entered in the new password and Confirm password fields, it displays the message, 'Confirm password does not match'
Verify entering the same password in both fields | 1. Navigate to the reset password page 2. Enter the same valid password in both new password and confirm password fields 3. Click the submit button | 1. Form should be submitted successfully 2. Password should be changed in the system 3. User should receive a confirmation that password has been changed 4. User should be redirected to the login page or automatically logged in | Pass | Pass | When same passwords are entered in the new password and Confirm password fields, form is submitted successfully and displays the message 'Password updated successfully'. But, user does not reecive a confirmation of the same. User is redirected to the login page | Password changed however yes confirmation message and but not taken to login page
Verify password strength requirements | 1. Navigate to the reset password page 2. Enter a weak password that doesn't meet requirements (e.g., too short, no special characters) 3. Enter the same weak password in confirm password field 4. Click the submit button | 1. Form should not be submitted 2. Validation messages should appear indicating which password requirements are not met 3. User should not be able to change their password until a stronger password is provided | Pass | Pass | Form is not submitted when weak password is entered in new and confirm password fields. Displays the message, 'Password must be at least 8 characters'
Verify entering the same password as the old password | 1. Navigate to the reset password page 2. Enter the user's current/old password in both fields 3. Click the submit button | 1. Form should not be submitted 2. A validation message should appear indicating that the new password cannot be the same as the old password 3. User should be prompted to choose a different password | Pass | Fail | Validation message does not appear when user's current /old password is entered in both fields. It accepts them and displays the message 'Password updated successfully' Also, user is not prompted to choose a different password | Fixed (MK) | still allows for the use of the same password as old one, test case failed (not fixed)
Verify password with minimum length requirement | 1. Navigate to the reset password page 2. Enter a password that is shorter than the minimum required length 3. Enter the same password in confirm password field 4. Click the submit button | 1. Form should not be submitted 2. A validation message should appear indicating the minimum length requirement 3. User should not be able to change their password until corrected | Pass | Pass | When a password shorter thatn the min required length is entered, it displays the message, 'Password must be at least 8 characters' and user cannot change their password until it is corrected
Verify password with maximum length requirement | 1. Navigate to the reset password page 2. Enter a password that exceeds the maximum allowed length 3. Enter the same password in confirm password field 4. Click the submit button | 1. Form should not be submitted 2. A validation message should appear indicating the maximum length requirement 3. User should not be able to change their password until corrected | Pass | Pass | The new and confirm password fields accept a max of 72 characters and the passwords are successfully updated. User also logs in with this lengthy password | fails, it took over 72 characters for me
Verify password complexity requirements | 1. Navigate to the reset password page 2. Test various passwords that fail to meet complexity requirements: a. Password without uppercase letter b. Password without lowercase letter c. Password without number d. Password without special character (if required) 3. Click the submit button after each test | 1. Form should not be submitted for any password that doesn't meet complexity requirements 2. Specific validation messages should appear for each failed requirement 3. User should not be able to change their password until all requirements are met | Pass | Pass | Form is not submitted for any password that does not meet complexity requirements. For any failed requirement, specific validation messages are displayed and user cannot change their password until all requirements are met
Verify successful password reset and login with new password | 1. Successfully reset password to a new valid password 2. Navigate to the login page 3. Enter username/email and the newly reset password 4. Click the login button | 1. User should be able to log in successfully with the new password 2. User should be redirected to the appropriate dashboard or home page | Pass | Pass | User can successfully login with newly reset password
Verify login with old password after reset | 1. Successfully reset password to a new valid password 2. Navigate to the login page 3. Enter username/email and the old password 4. Click the login button | 1. Login should fail 2. A validation message should appear indicating invalid credentials 3. User should not be able to access the system with the old password | Pass | Pass | Login fails when email and the old password are entered in login page.
Verify password reset link validity after successful reset | 1. Successfully reset password using a reset link 2. Try to use the same reset link again | 1. The reset link should be invalidated after a successful password reset 2. Attempting to use it again should result in an error message 3. User should be directed to request a new reset link if needed | Pass | Pass | The reset link is invalidated after a successful password reset.
Verify copy-paste functionality in password fields | 1. Navigate to the reset password page 2. Type a valid password in the new password field 3. Copy the password 4. Paste it into the confirm password field 5. Click the submit button | 1. Copy-paste functionality should work if not explicitly disabled for security reasons 2. If functionality works, password should be reset successfully 3. If disabled for security, appropriate message should be displayed | Pass | Pass | Copy-paste functionality works in password fields and the password is reset successfully | no errors (maybe copy paste functionality should be removed for security and privacy)
Verify password visibility eye icon | 1. Navigate to the reset password page 2. Enter a password in either field 3. Click on the password visibility toggle icon (eye icon) | 1. If toggle is available, password should become visible when clicked 2. Clicking again should hide the password 3. The functionality should work independently for both password fields | Pass | Pass | Toggle is available and password is visible and when clicked again, it becomes hidden. Functionality workd independently for both password fields | no errors but masking works but I think the eye should be cancelled when its the dots and not canceled when you are able to see the password
Verify reset password functionality with keyboard navigation | 1. Navigate to the reset password page 2. Use Tab key to navigate through form elements 3. Use Enter key to submit the form with valid matching passwords | 1. User should be able to navigate through all form elements using the Tab key 2. User should be able to submit the form using the Enter key 3. Password should be reset successfully | Pass | Pass | User is able to navigate through all form elements using the Tab key. User is able to submit the form using the Enter key anf the password is reset successfully
Verify special characters in passwords | 1. Navigate to the reset password page 2. Enter a password with special characters in both fields 3. Submit the form | 1. System should handle special characters in passwords correctly 2. Password should be reset successfully 3. User should be able to log in with the new password containing special characters | Pass | Pass | System handles special characters in passwords correctly and Password is reset successfully. User is able to log in with the new password containing special characters

## Receptionist Signup
Description | Test Steps | Expected Output | Status | Test Status | Comments |  | Neha's Comments
Verify all mandatory elements are present on the welcome screen | 1. Login to the receptionist portal 2. Navigate to the welcome screen 3. Observe all UI elements | 1. All mandatory elements should be present: - Logo - Check-in option - Logout option - Settings option - Language selection option 2. All elements should be properly displayed and aligned | Pass | Pass | Mandatory elements are present, and are properly displayed and aligned
Verify logo display and functionality | 1. Observe the logo on the welcome screen 2. Click on the logo (if it's clickable) | 1. Logo should be clearly visible 2. If logo is designed to be clickable, it should navigate to the home/welcome screen or perform its designated function | Pass | Pass | Logo is clearly visible but not clickable
Verify logout option visibility and functionality | 1. Observe the logout option on the welcome screen 2. Click on the logout option | 1. Logout option should be clearly visible and accessible 2. Upon clicking, user should be logged out of the system 3. User should be redirected to the login page | Pass | Pass | Logout option is visible on the welcome screen and upon clicking it, user is logged out and redirected to the login page
Verify language selection option visibility and functionality | 1. Observe the language selection option on the welcome screen 2. Click on the language selection option 3. Select a different language | 1. Language selection option should be clearly visible and accessible 2. Upon clicking, a dropdown of available languages should appear 3. Selecting a different language should change the interface language accordingly | Pass | Pass | Language selection option is visible on the welcome screen and upon clicking it available languages appear. Upon selection of a language from the dropdown, the interface language changes accordingly
Verify welcome message or username display | 1. Login with a receptionist account 2. Observe the welcome screen | 1. A welcome message or the username should be displayed 2. The message should be personalized with the user's name | Pass | Fail | When logged in with a receptionist account, the welcome screen is displayed, but does not show a personalized message with the user's name. | Fixed (SV) | no personalized receptionist name
Verify navigation menu functionality | 1. Observe the navigation menu on the welcome screen 2. Click on each menu item | 1. All navigation menu items should be visible and accessible 2. Clicking on each item should navigate to the corresponding page 3. Each destination page should load correctly | Pass | Pass | All navigation menu items are visible and accessible and clicking on each of them navigates to the corresponding destination page
Verify visitor management page access from check-in option | 1. Click on the check-in option from the welcome screen 2. Observe the visitor management page | 1. User should be navigated to the visitor management page 2. Visitor management page should load completely 3. All visitor management functions should be accessible | Pass | Fail | When the check-in option from the welcome screen is clicked, user is navigated to the Visitor Information page. Visitor management functions are not displayed | Fixed (SV) | no visitor management page just information page (need clarity on what this is)
Verify welcome screen responsiveness | 1. Access the welcome screen on different devices with varying screen sizes 2. Observe the layout and accessibility of elements | 1. Welcome screen should be responsive 2. All elements should adjust appropriately to different screen sizes 3. No elements should be cut off or inaccessible on smaller screens | Pass |  | Needs testing on different devices
Verify welcome screen performance | 1. Login to the receptionist portal 2. Observe the load time for the welcome screen | 1. Welcome screen should load quickly (within acceptable time limits) 2. All elements should render without delays 3. No performance issues should be observed | Pass | Pass | Welcome screen loads quickly and all elements are rendered without delays.
Verify welcome screen after refresh | 1. Login to the receptionist portal 2. Refresh the browser on the welcome screen | 1. Welcome screen should reload properly 2. User should remain logged in 3. All elements should display correctly after refresh | Pass |  | Needs testing on broswer
Verify without entering any data and click on the submit button | 1. Login to the receptionist portal 2. Clicks to submit button | 1.The validation message should indicate that one or more mandatory fields are missing. 2. The validation message could specify which particular fields are required (e.g., "Name is required," "Email is required"). | Pass | Pass | Clicking on submit button without entering any data, displays a validation message for the first empty field encounterd in the form and as they are filled while leaving other fields empty and clicking on submit/signup button
Verify that you entered an invalid email and click on the submit button | 1. Login to the receptionist portal 2. Clicks to submit button | 1.The validation message should indicate that one or more mandatory fields are missing. 2. The validation message could specify which particular fields are required. | Pass | Pass | Validation message is displayed for the missing mandatory fields
Verify try to enter an alphabet value in the phone number field. | 1. Login to the receptionist portal 2. Clicks to submit button | 1. User should not be able to enter 2. Phone number field should be numeric | Pass | Pass | User is not able to enter alphabet value in the phone number
Verify, enter with a different password in both fields, confirm, and the new password field. | 1. Login to the receptionist portal 2. Clicks to submit button | 1.The validation message should indicate that one or more mandatory fields are missing. 2. Both field should have same password | Pass | Pass | Displays a validation message when Password and Confirm Password fields have different passwords
Verify that using all valid data and clicking on the submit button. | 1. Login to the receptionist portal 2. Clicks to submit button | 1.The validation message should indicate that one or more mandatory fields are missing. 2. The validation message could specify which particular fields are required. | Pass | Pass | When valid data is entered and submit button is clicked, a validation message is displayed for any missing mandatory fields
Verify successful account creation with valid data | 1. Navigate to the receptionist signup page. 2. Enter valid data in all required fields (First Name, Last Name, Email, Phone Number, Password, Confirm Password). 3. Click the 'Submit' button. | The account should be created successfully, and the user should be navigated to the welcome screen or home page. | Pass | Pass | On successful account creation, user is navigated to the home page or welcome page

## Check-in
Description | Test Steps | Expected Result | Status | Test Status | Comments |  | Neha's Comments
Verify navigation to visitor check-in page | 1. Click on the check-in button/option | User is navigated to the visitor check-in page | Pass | Pass | User is navigated to visitor check-in page when Check-in button is clicked
Verify validation for empty mandatory fields | 1. Navigate to visitor check-in page 2. Leave all fields empty 3. Click on the submit button | Validation message appears indicating mandatory fields must be filled | Pass | Pass | When all fields are empty, validation message appears indicating mandatory fields must be filled
Verify all mandatory fields are present | 1. Navigate to visitor check-in page | All mandatory fields are displayed: Name, Email, Phone Number, Company Name, Purpose of Visit, and Host Name | Pass | Pass | All mandatory fields are present
Verify validation for individual empty fields - Name | 1. Navigate to visitor check-in page 2. Leave Name field empty 3. Fill all other mandatory fields 4. Click on the next button | Validation message appears for the Name field | Pass | Pass | Filling all fields but Name field, displays validation message for the field
Verify validation for individual empty fields - Email | 1. Navigate to visitor check-in page 2. Leave Email field empty 3. Fill all other mandatory fields 4. Click on the next button | Validation message appears for the Email field | Pass | Pass | Filling all fields but Email field, displays validation message for the field
Verify validation for individual empty fields - Phone Number | 1. Navigate to visitor check-in page 2. Leave Phone Number field empty 3. Fill all other mandatory fields 4. Click on the next button | Validation message appears for the Phone Number field | Pass | Pass | Filling all fields but Phone Number field, displays validation message for the field
Verify validation for individual empty fields - Company Name | 1. Navigate to visitor check-in page 2. Leave Company Name field empty 3. Fill all other mandatory fields 4. Click on the next button | Validation message appears for the Company Name field | Pass | Pass | Filling all fields but Company Name field, displays validation message for the field
Verify validation for individual empty fields - Purpose of Visit | 1. Navigate to visitor check-in page 2. Leave Purpose of Visit field empty 3. Fill all other mandatory fields 4. Click on the next button | Validation message appears for the Purpose of Visit field | Pass | Pass | Filling all fields but Purpose of Visit field, displays validation message for the field
Verify validation for individual empty fields - Host Name | 1. Navigate to visitor check-in page 2. Leave Host Name field empty 3. Fill all other mandatory fields 4. Click on the next button | Validation message appears for the Host Name field | Pass | Pass | Filling all fields but Host Name field, displays validation message for the field
Verify validation for invalid email format | 1. Navigate to visitor check-in page 2. Enter invalid email format (e.g., "test@") 3. Fill all other mandatory fields 4. Click on the next button | Validation message appears indicating invalid email format | Pass | Pass | All mandatory fields are filled. Invalid email format (Ex: user@, user@gmail, @gmail.com, @gmail) displayed validation message indicating the same
Verify searching for a host from another entity | 1. Navigate to visitor check-in page 2. Search for a host from another entity | No host should be found/displayed from another entity | Pass | Pass | Host from another entity is not displayed
Verify validation for invalid host name | 1. Navigate to visitor check-in page 2. Enter an invalid/non-existent host name 3. Fill all other mandatory fields 4. Click on the next button | Validation message appears indicating invalid host name | Pass | Pass | When invalid / non-existent host name is entered with all mandatory fields filled, validation message 'Please select host name' appears
Verify phone number field accepts only numeric values | 1. Navigate to visitor check-in page 2. Attempt to enter alphabetic characters in the phone number field | User is unable to enter alphabetic characters in the phone number field | Pass | Pass | Phone Number field does not accept alphabetic characters
Verify phone number field minimum length validation | 1. Navigate to visitor check-in page 2. Enter phone number with fewer digits than required 3. Fill all other mandatory fields 4. Click on the next button | Validation message appears indicating phone number is too short | Pass | Pass | Phone Number with length less than 7 digits is not being accepted. Displays the message 'Mobile number must be 7 digit long'
Verify phone number field maximum length validation | 1. Navigate to visitor check-in page 2. Attempt to enter more digits than the maximum allowed for phone number | Phone number field should not accept more than the maximum allowed digits | Pass | Pass | Phone Number field does not accept more than 14 digits
Verify navigation to camera screen after entering valid data | 1. Navigate to visitor check-in page 2. Enter all valid mandatory data 3. Click on the next button | User is navigated to the camera screen | Pass | Pass | After all mandatory fields are entered with valid data, user is navigated to Waiver Policy. Then, when the Agree button is clicked, user is navigated to camera screen.
Verify navigation from camera screen to review screen | 1. Complete the visitor check-in form 2. Navigate to camera screen 3. Capture image 4. Click on the next button | User is navigated to the review and confirmation screen | Pass | Pass | User is navigated to the review and confirmation screen after the image is captured and the tick mark button in Edit Photo is clicked.
Verify ability to edit visitor details from review screen | 1. Navigate to review and confirmation screen 2. Click on the edit option | User is able to edit all visitor details (host name, phone number, company name, etc.) | Pass | Pass | User is able to edit all visitor details (host name, phone number, company name, etc.) in confirmation screen when Edit button is clicked
Verify navigation after confirming visitor details | 1. Navigate to review and confirmation screen 2. Click on the confirm button | User is navigated to the notification status screen followed by the visitor badge display within 2-3 seconds | Pass | Fail | When Confirm button is clicked and an email is sent to host, the visitor badge is not displayed | error get a message saying unable to notify and there is an error
Verify visitor badge printing process | 1. Complete visitor check-in process 2. Reach the confirmation screen where badge is displayed | Visitor badge is printed by the printer | Pass | Fail | Visitor badge printing - not tested as confirmation screen where badge is displayed does not appear | no confirmation page so not tested and not seen
Verify host email notification | 1. Complete visitor check-in process with a valid host selection 2. Confirm visitor details | Selected host receives an email notification about the visitor check-in | Pass | Fail | Not able to check if the host receives an email notification | do not see email and no way to check and be sure
Verify character limit for Name field | 1. Navigate to visitor check-in page 2. Attempt to enter more characters than allowed in the Name field | Name field should not accept more than the maximum allowed characters | Pass | Pass | Name field accepts a maximum of 81 characters | took more than 81 characters
Verify character limit for Company Name field | 1. Navigate to visitor check-in page 2. Attempt to enter more characters than allowed in the Company Name field | Company Name field should not accept more than the maximum allowed characters | Pass | Pass | Company Name field accepts more than 4000 characters
Verify host search functionality with partial name | 1. Navigate to visitor check-in page 2. Enter partial name of a host in the Host Name field | Matching hosts should be displayed in the search results | Pass | Pass | Entering partial name of a host in Host Name field displays matching hosts in search results
Verify host selection from search results | 1. Navigate to visitor check-in page 2. Search for a host 3. Select a host from the search results | Selected host should be displayed in the Host Name field | Pass | Pass | When host name is selected from the search results, it is displayed in the Host Name field
Verify cancellation of check-in process | 1. Start the visitor check-in process 2. Click on cancel/back button at any stage | User should be navigated back to the home/landing page | Pass | Fail | User can only click the Back button and navigate to the previous page. It does not navigate to the home/landing page when back button is clicked.
Verify navigation back from camera screen | 1. Complete the visitor check-in form 2. Navigate to camera screen 3. Click on back button | User should be navigated back to the visitor details form with previously entered data preserved | Pass | Pass | User is navigated back to the visitor details form with previously entered data preserved when he clicks on the back button and navigates from camera screen.
Verify retaking photo option | 1. Complete the visitor check-in form 2. Navigate to camera screen 3. Capture image 4. Click on retake photo option | User should be able to capture a new photo | Pass | Pass | User is able to capture a new photo by clicking on Retake photo option
Verify special characters validation in Name field | 1. Navigate to visitor check-in page 2. Attempt to enter special characters in the Name field | System should either prevent entry or show validation message based on requirements | Pass | Pass | System prevents user from entering special characters in the Name field
Verify special characters validation in Company Name field | 1. Navigate to visitor check-in page 2. Attempt to enter special characters in the Company Name field | System should either prevent entry or show validation message based on requirements | Pass | Pass | System does not prevent user from entering special characters in the Company Name field | Fail
Verify email field accepts valid email format with special characters | 1. Navigate to visitor check-in page 2. Enter valid email with special characters (e.g., "test.name+tag@example.com") | Email field should accept the valid format | Pass | Pass | Email field accepts the valid email with special characters like ., +, -
Verify visitor badge includes all required information | 1. Complete visitor check-in process 2. View the generated visitor badge | Badge should display visitor name, host name, date, time, and any other required information | Pass | Fail | Visitor badge is not displayed | Fixed | No badge seen, fail
Verify editing visitor photo from review screen | 1. Navigate to review and confirmation screen 2. Attempt to edit visitor photo | User should be able to retake visitor photo if the feature is supported | Pass | Pass | User is able to retake visitor photo when on the confirmation screen
Verify the check-in process when network connectivity is slow | 1. Simulate slow network connectivity 2. Perform visitor check-in process | Check-in process should complete successfully with appropriate loading indicators | Pass | Pass | Check-in process completes successfully with appropriate loading indicators when network connectivity is slow
Verify duplicate check-in prevention for the same visitor on same day | 1. Complete check-in for a visitor 2. Attempt to check-in the same visitor (identical details) on the same day | System should either prevent duplicate check-in or handle it according to business requirements | Pass | Pass | When same visitor attempts to check in on the same day, it displays the message 'This email already check in by user. Please use another email'
Verify visitor checkout process if applicable | 1. Complete visitor check-in process 2. Initiate visitor checkout process | Visitor checkout should be recorded and host should be notified if required | Pass | Pass | Visitor checkout is recorded. Not able to check if host is notified of the same though it shows the message 'Sending notification to MGM Host 1' | Fail | not able because of error that says sending notification to MGM host (confirm with sindu)

## Check-out
Description | Test Steps | Expected Result | Status | Test Status | Comments | Comments | Neha's Comments
Verify navigation to visitor checkout page | 1. Click on the checkout button/option | User is navigated to the visitor checkout screen | Pass | Pass | User is navigated to the visitor checkout what the checkout button /option
Verify all mandatory fields are present on checkout page | 1. Navigate to the visitor checkout page | Email field and verify button should be present on the page | Pass | Pass | Email field and verify button are present on the page
Verify validation for empty email field | 1. Navigate to the visitor checkout page 2. Leave email field empty 3. Click on the verify button | Validation message appears indicating email field is required | Pass | Pass | When email field is left empty, it displays the message, 'Please enter an email address'
Verify validation for invalid email format | 1. Navigate to visitor checkout page 2. Enter invalid email format (e.g., "test@") 3. Click on the verify button | Validation message appears indicating invalid email format | Pass | Pass | When an email (like test@) is entered, it displays, ' 'Please enter a valid email address''
Verify validation when using email from another entity | 1. Navigate to visitor checkout page 2. Enter an email address associated with another entity 3. Click on the verify button | Validation message appears indicating email not found or not valid for checkout | Pass | Pass | When an email address associated with another entity is entered, a validation message appears indicating email is not found.
Verify successful email verification | 1. Navigate to visitor checkout page 2. Enter valid email of a checked-in visitor 3. Click on the verify button | Active session field appears showing visitor's check-in time | Pass | Pass | When Find Active Session button is clicked for a valid email of a checked-in visitor, it shows the visitor's check-in time
Verify checkout button functionality | 1. Navigate to visitor checkout page 2. Enter valid email of a checked-in visitor 3. Click on the verify button 4. Once check-in time is fetched, click on the checkout button | Visitor is successfully checked out with confirmation message | Pass | Pass | When check-out button is clicked after the check-in time is fetched, visitor is successfully checked out with confirmation message 'Check-Out completed' and Finish button.
Verify prevention of duplicate checkout | 1. Successfully check out a visitor 2. Attempt to check out the same visitor again using the same email | System should prevent duplicate checkout or show an appropriate message indicating visitor is already checked out | Pass | Pass | System prevents duplicate checkout and displays the message 'Visitor is not in a exits. Please check the details and try again'
Verify checkout status is updated in system | 1. Successfully check out a visitor 2. Check visitor status in the system (via admin panel or database) | Visitor status should be updated to 'checked out' with accurate checkout timestamp | Pass | Fail | When the visitor is checked out, it displays the screen for Check-out complete. In the admin panel, it shows the check-out time, but shows the Visitor Request Status as ‘Pending’ | Fixed | status still shows pending but shows check out time
Verify checkout without prior check-in | 1. Navigate to visitor checkout page 2. Enter valid email of a person who has not checked in 3. Click on the verify button | System should display appropriate message indicating no active check-in found for the email | Pass | Pass | Displays the message 'Visitor is not in a exits. Please check the details and try again' when no active check-in found for the email
Verify checkout UI responsiveness | 1. Navigate to visitor checkout page 2. Test on different screen sizes/resolutions | Checkout page UI should be responsive and properly formatted across different screen sizes | Pass |  | Needs testing on different screens
Verify cancel/back functionality | 1. Navigate to visitor checkout page 2. Click on cancel/back button | System should return to the home/landing page | Pass | Pass | Clicking on the back button, system returns to the landing page
Verify case sensitivity of email field | 1. Navigate to visitor checkout page 2. Enter valid email with different case (e.g., "Test@example.com" instead of "test@example.com") 3. Click on the verify button | System should handle email in a case-insensitive manner and find the visitor | Pass | Pass | System handles the email in a case-insensitive manner and finds the visitor
Verify checkout process with slow network connectivity | 1. Simulate slow network connectivity 2. Perform visitor checkout process | Checkout process should complete successfully with appropriate loading indicators | Pass |  | Need to be test with slow network connectivity
Verify checkout completion notification | 1. Successfully complete the checkout process | System should display clear confirmation that checkout is successful | Pass | Pass | System displays confirmation message on successful checkout

## Recept. Sign up New
Description | Test Steps | Expected Output | Status | Test Status | Comments | Neha's Comments
Register Receptionist - Valid Data Full Details | 1. Navigate to registration page 2. Enter First Name: John 3. Enter Last Name: Doe 4. Enter Valid Email: john.doe@company.com 5. Enter Valid Phone Number: +1234567890 6. Select Location: New York 7. Select Entity: Hospital 8. Enter Strong Password: P@ssw0rd123! 9. Confirm Password: P@ssw0rd123! 10. Click Submit | Registration Successful - Account Created | Pass | Pass | Registration is successful when account is created after all form fields are filled
Mismatched Passwords Validation | 1. Navigate to registration page 2. Enter First Name: John 3. Enter Last Name: Doe 4. Enter Valid Email: john.doe@company.com 5. Enter Valid Phone Number: +1234567890 6. Select Location: New York 7. Select Entity: Hospital 8. Enter Password: StrongPass123! 9. Enter Confirm Password: DifferentPass456@ 10. Click Submit | Validation message appears: Passwords do not match, Registration prevented | Pass | Pass | When passwords do not match, a validation message appears and prevents the registration process.
First Name Validation - Minimum Length | 1. Navigate to registration page 2. Enter First Name: J 3. Enter Last Name: Doe 4. Enter Valid Email: john.doe@company.com 5. Enter Valid Phone Number: +1234567890 6. Select Location: New York 7. Select Entity: Hospital 8. Enter Strong Password: P@ssw0rd123! 9. Confirm Password: P@ssw0rd123! 10. Click Submit | Validation message appears: First name must be at least 2 characters long | Pass | Fail | It accepts a First Name having a single character and creates the account
First Name Validation - Empty Field | 1. Navigate to registration page 2. Leave First Name blank 3. Enter Last Name: Doe 4. Enter Valid Email: john.doe@company.com 5. Enter Valid Phone Number: +1234567890 6. Select Location: New York 7. Select Entity: Hospital 8. Enter Strong Password: P@ssw0rd123! 9. Confirm Password: P@ssw0rd123! 10. Click Submit | Validation message appears: First name is required | Pass | Pass | When First Name field is left blank while all other fields are filled, it displays the message 'Please enter first name'
Last Name Validation - Minimum Length | 1. Navigate to registration page 2. Enter First Name: John 3. Enter Last Name: D 4. Enter Valid Email: john.doe@company.com 5. Enter Valid Phone Number: +1234567890 6. Select Location: New York 7. Select Entity: Hospital 8. Enter Strong Password: P@ssw0rd123! 9. Confirm Password: P@ssw0rd123! 10. Click Submit | Validation message appears: Last name must be at least 2 characters long | Pass | Fail | It accepts a Last Name having a single characted and creates the account | Will allow again one character
Last Name Validation - Empty Field | 1. Navigate to registration page 2. Enter First Name: John 3. Leave Last Name blank 4. Enter Valid Email: john.doe@company.com 5. Enter Valid Phone Number: +1234567890 6. Select Location: New York 7. Select Entity: Hospital 8. Enter Strong Password: P@ssw0rd123! 9. Confirm Password: P@ssw0rd123! 10. Click Submit | Validation message appears: Last name is required | Pass | Pass | Validation message is displayed when the last name field is left blank
Email Validation - Invalid Format | 1. Navigate to registration page 2. Enter First Name: John 3. Enter Last Name: Doe 4. Enter Invalid Email: john.doe.company 5. Enter Valid Phone Number: +1234567890 6. Select Location: New York 7. Select Entity: Hospital 8. Enter Strong Password: P@ssw0rd123! 9. Confirm Password: P@ssw0rd123! 10. Click Submit | Validation message appears: Invalid email format | Pass | Pass | Validation message is displayed when an invalid email (like user@gmail ) is entered
Email Validation - Empty Field | 1. Navigate to registration page 2. Enter First Name: John 3. Enter Last Name: Doe 4. Leave Email blank 5. Enter Valid Phone Number: +1234567890 6. Select Location: New York 7. Select Entity: Hospital 8. Enter Strong Password: P@ssw0rd123! 9. Confirm Password: P@ssw0rd123! 10. Click Submit | Validation message appears: Email is required | Pass | Pass | Displays a validation message 'Please enter an email address' when the email field is left blank
Email Validation - Duplicate Email | 1. Navigate to registration page 2. Enter First Name: John 3. Enter Last Name: Doe 4. Enter Existing Email: john.doe@company.com 5. Enter Valid Phone Number: +1234567890 6. Select Location: New York 7. Select Entity: Hospital 8. Enter Strong Password: P@ssw0rd123! 9. Confirm Password: P@ssw0rd123! 10. Click Submit | Validation message appears: Email already registered | Pass | Pass | Displays a validation message 'The email is already take by a user'
Phone Number Validation - Invalid Format | 1. Navigate to registration page 2. Enter First Name: John 3. Enter Last Name: Doe 4. Enter Valid Email: john.doe@company.com 5. Enter Invalid Phone Number: 123 6. Select Location: New York 7. Select Entity: Hospital 8. Enter Strong Password: P@ssw0rd123! 9. Confirm Password: P@ssw0rd123! 10. Click Submit | Validation message appears: Invalid phone number format | Pass | Pass | When a phone number with 3 digits is entered, it displays the validation message 'Mobile number must be 7 digits long'
Phone Number Validation - Empty Field | 1. Navigate to registration page 2. Enter First Name: John 3. Enter Last Name: Doe 4. Enter Valid Email: john.doe@company.com 5. Leave Phone Number blank 6. Select Location: New York 7. Select Entity: Hospital 8. Enter Strong Password: P@ssw0rd123! 9. Confirm Password: P@ssw0rd123! 10. Click Submit | Validation message appears: Phone number is required | Pass | Pass | Displays a validation message 'Please enter a phone number', when the phone number field is left blank
Location Validation - Not Entered | 1. Navigate to registration page 2. Enter First Name: John 3. Enter Last Name: Doe 4. Enter Valid Email: john.doe@company.com 5. Enter Valid Phone Number: +1234567890 6. Leave Location Not Entered 7. Select Entity: Hospital 8. Enter Strong Password: P@ssw0rd123! 9. Confirm Password: P@ssw0rd123! 10. Click Submit | Validation message appears: Location is required | Pass |  | The Location field is not present in the form | No such thing as location on form
Entity Validation - Not Selected | 1. Navigate to registration page 2. Enter First Name: John 3. Enter Last Name: Doe 4. Enter Valid Email: john.doe@company.com 5. Enter Valid Phone Number: +1234567890 6. Select Location: New York 7. Leave Entity unselected 8. Enter Strong Password: P@ssw0rd123! 9. Confirm Password: P@ssw0rd123! 10. Click Submit | Validation message appears: Entity is required | Pass |  | There is no option to select an entity | Have to type something in for the entity to options to show up and select from no option to directly select
Password Validation - Weak Password | 1. Navigate to registration page 2. Enter First Name: John 3. Enter Last Name: Doe 4. Enter Valid Email: john.doe@company.com 5. Enter Valid Phone Number: +1234567890 6. Select Location: New York 7. Select Entity: Hospital 8. Enter Weak Password: password 9. Confirm Password: password 10. Click Submit | Validation message appears: Password is too weak (must contain uppercase, lowercase, number, and special character) | Pass | Pass | When a password like 'abcdefgh' is entered, it displays a validation message 'Password must have at least 8 characters that include at least 1 lowercase, 1 uppercase'
Special Characters in Name Fields | 1. Navigate to registration page 2. Enter First Name: John@ 3. Enter Last Name: Doe# 4. Proceed with other valid details 5. Click Submit | Validate handling of special characters in name fields | Pass | Pass | First Name and Last Name fields do not allow special characters to be entered.
Numeric Input in Name Fields | 1. Navigate to registration page 2. Enter First Name: John123 3. Enter Last Name: Doe456 4. Proceed with other valid details 5. Click Submit | Validate handling of numeric input in name fields | Pass | Pass | First Name and Last Name fields do not allow digits to be entered.
Long Input Validation | 1. Navigate to registration page 2. Enter extremely long inputs in all fields 3. Proceed with registration | Validate input length restrictions and proper truncation/handling | Pass | Pass | Accepts upto 26 letters for First Name and and Last Name, upto 100 for email, and 14 for Phone Number

## Recept.login New
Description | Test Steps | Expected Output | Status | Test Status | Comments | Neha's Comments
Login - Valid Credentials | 1. Open Login Page 2. Enter Registered Email: john.doe@company.com 3. Enter Correct Password: P@ssw0rd123! 4. Click Login | Successfully Navigate to site Selection Popup | Pass | Pass | Entering valid credentials on login page successfully navigated to site selection popup.
Login - Invalid Email Format | 1. Open Login Page 2. Enter Invalid Email: john.doe.company 3. Enter Password: P@ssw0rd123! 4. Click Login | Display Validation Error: Invalid Email Format | Pass | Pass | Entering invalid email displays validation error message 'Please enter valid address'
Login - Unregistered Email | 1. Open Login Page 2. Enter Unregistered Email: unknown@company.com 3. Enter Any Password 4. Click Login | Display Error: Email Not Registered | Pass | Pass | Entering an unregistered email address, displays error message 'The email does not exist'
Login - Incorrect Password | 1. Open Login Page 2. Enter Registered Email: john.doe@company.com 3. Enter Incorrect Password: WrongPassword123 4. Click Login | Display Error: Invalid Credentials | Pass | Pass | Entering incorrect password displays error messge indicatin that the provided credentials are incorrect
Site Selection - No Site Selected | 1. Complete Login 2. Open Site Selection Popup 3. Click Submit Without Selecting site | Display Validation Error: Site Selection Required | Pass | Pass | On Site Selection Popup, when site is not selected, it displays the message 'Please select site name'
Site Selection - Valid Site Selected | 1. Complete Login 2. Open Site Selection Popup 3. Select One Site 4. Click Submit | Successfully Navigate to Receptionist Dashboard | Pass | Pass | When site is selected in the popup, it successfully navigates to the Receptionist dashboard page
Password Reset Flow | 1. Open Login Page 2. Click Forgot Password 3. Enter Registered Email 4. Receive Reset Link 5. Click Reset Link 6. Enter New Password 7. Confirm New Password | Successfully Reset Password and Able to Login | Pass | Pass | Password is being reset successfully and able to login
Device Compatibility Check | 1. Test Login on Different Mobile Devices 2. Verify Responsive Design 3. Check All Functionalities | Consistent UI and Functionality Across Devices | Pass |  | Need testing on different mobile devices | needs to be checked in another device than just the laptop